## Tasks
EEET2580 Teamwork Contribution Document
SQUAD TIGER - GROUP [B]
| Name: Nguyen Duc Anh |  |  | Name: Dang Vinh Luan |  |  | Name: Tran Xuan Hoang Dat |  |  | Name: Luong Gia Bao |  |  | Name: Le Thanh Vinh
| Assigned Tasks | Date Start | Date Completed | Assigned Tasks | Date Start | Date Completed | Assigned Tasks | Date Start | Date Completed | Assigned Tasks | Date Start | Date Completed | Assigned Tasks | Date Start | Date Completed
MILESTONE 1
Architecture Design | BE Architecture Design |  |  | FE Architecture Design |  |  | BE Architecture Review |  |  | BE Architecture Design |  |  | FE Architecture Design
MILESTONE 2
UX / UI Design | Figma Review |  |  | Figma Review |  |  | Figma Review |  |  | Figma Review |  |  | Figma Design
Front-end Development |  |  |  | Admin Settings Page | 2025-01-01 | 2025-01-10 | [6 empty] | Admin Statistics Page | 2025-01-01 | 2025-01-10
|  |  |  | Admin Project Management Page | 2025-01-01 | 2025-01-11 | [6 empty] | Admin Users Management Page | 2025-01-02 | 2025-01-04
|  |  |  | Admin Add Image Function | 2025-01-01 | 2025-01-11 | [6 empty] | Admin Dashboard Page | 2025-01-01 | 2025-01-07
|  |  |  | Add Project Form | 2025-01-05 | 2025-01-07
|  |  |  | Fetch image from database | 2025-01-06 | 2025-01-08 | [6 empty] | Authentication for frontend | 2025-01-09 | 2025-01-13
|  |  |  | Send Email to Charities | 2025-01-06 | 2025-01-12 | [6 empty] | Add Donors Form | 2025-05-05 | 2025-01-06
[13 empty] | Add Charity Form | 2025-01-05 | 2025-01-07
Back-end Development | Donor Service | 2024-12-14 | 2025-01-05 |  |  |  | Donors Module | 2024-12-20 | 2024-12-29 | Authentication Service | 2025-01-02 | 2025-01-11
| Charity Service | 2024-12-14 | 2025-01-05 |  |  |  | API-gateway/ Key request Team A | 2024-12-18 | 2024-12-29 | Statistic Service | 2025-01-08 | 2025-01-11
| Caching with Redis | 2024-12-19 | 2025-01-08 |  |  |  | API-gateway/ Payment request Team A | 2025-01-05 | 2025-01-05 | Migrate the system from Monolith to Microservices | 2024-12-13 | 2024-12-19
| Database Connection Setup | 2024-12-07 | 2024-12-07 |  |  |  | API-gateway/ Encryption request Team A | 2025-01-01 | 2025-01-02 | API-Gateway/ Authentication Middleware | 2025-01-12 | 2025-01-13
| Message Broker (Kafka) setup | 2024-12-12 | 2024-12-16 |  |  |  | API-gateway/ Email request Team A | 2025-01-05 | 2025-01-05 | API-Gateway/ Auth Request | 2025-01-13 | 2025-01-14
| API-Gateway charity requests setup | 2024-12-10 | 2024-12-27 |  |  |  | API-gateway/ Project request Team A | 2025-01-07 | 2025-01-05 | API-Gateway/Statistic Request
| API-Gateway donor requests setup | 2024-12-10 | 2024-12-27 |  |  |  | API-gateway/ Decryptionrequest Team A | 2025-01-06 | 2025-01-07 | API-Gateway/Internal Routes
| API-Gateway Kafka service setup | 2024-12-15 | 2024-12-16 |  |  |  | Testing API
| API-Gateway Logging Middleware | 2024-12-16 | 2024-12-17 |  |  |  | Write ReadME
Reporting | C4 diagrams redraw | 2025-01-11 | 2025-01-12 |  |  |  | Report Wrting/ C4 Diagram | 2025-01-09 | 2025-01-10
| ERD redraw | 2025-01-11 | 2025-01-12 |  |  |  | Report Wrting/Service Breakdown | 2025-01-11 | 2025-01-11
Repository | Team-B repository |  |  |  |  | API-Gateway Repository